## Lessons Learned Template
Lessons Learned Template
Today's Date: | 2026-09-02
Project Name: | Homelab Enterprise Infrastructure Deployment
Project Manager: | Jeremy Beckley
Version: | 1.0.0
WIN or ISSUE | Describe What Happened | What Was the Impact? | How Does This Change Future Projects? | Action Items
WIN | Introduction to the Project Manager Role What is a project? Project vs Operations Project manager responsibilities Project lifecycle Server rooms Data Center Types | Positive; I was able to get a better understanding of what to expect when it comes to PM responsibility and the makings of a Data Center | This allows me to be have a deeper understanding of what to expect so nothing feels too overwhelming | Memorize
WIN | Project Charter Creation Purpose Scope Objective Risk Authority | Positive; I was able to create a strong foundation for my upcoming project and the services it will be providing to varying industry level stakeholders | This allows me to be more confident with my decisions moving forward due to me understanding the direction I am trying to go | Iterate
ISSUE | Fast Tracking Day 5-7 | Negative; I was able to combine work parallel to catch up with the schedule, however this posses possible issues such as unnecessary complexity, resource strain, and possible quality compromise | I am able to better feel how my future project team might feel about fast tracking their workload, ensuring a better working environment | Monitor
WIN | Project Objectives and Success Criteria Project Objective Assumptions Constraints Success Criteria | Positive; I was able to have an understanding of what actions might limit the project and what I can assume ahead of time | This allows me to be better prepared for issues that might come up and understand where I can update this information as I move forward in the project | Iterate
WIN | Stakeholder Management Stakeholders Stakeholder Analysis Stakeholder Engagement Stakeholder Register | Positive; I was able to understand how to identify stakeholder, manage them and properly track them | This allows me to better understand who it is I will be working with, what typical data center project must deliver and how to better track engagement so we do not loose out on our investors | Iterate
WIN
WIN
ISSUE
ISSUE
WIN
WIN

## How to Use This Template
How to Use Our Lessons Learned Template
The lessons learned template is a tool to note what worked and what didn't in your project to repeat the positive and avoid the negative.
Today's Date: Enter today’s date
Project Name: Give your project a name, so it can be quickly identified
Project Manager: Enter the name of the person overseeing the project. This could be a proper project manager or any staff member who is the owner of the work.
Notes: This field is for you to add any relevant information you’d like. Ideas: client name, stakeholders, project summary, budget, etc.
WIN or ISSUE: Choose either WIN or ISSUE to classify the lesson. A win is something positive that happened, and an issue is something negative that happened
Describe What Happened: Use this field to give a detailed description of the lesson you learned
What Was the Impact?: Here, you’ll describe the positive or negative result, and the impact there may have been. For a win, write about the positive outcome that occurred. For an issue, write about the negative consequences you experienced due to the problem
How Does This Change Future Projects?: In this field, record your thoughts on how this lesson might impact future work. Think about how other people in your organization might benefit from learning this lesson
Action Items: Add the actionable steps that will be taken to address your win or issue. Every row should have an action item, even if it is as simple as “monitor to see if it happens again.” This is the most important part of the template, because you are outlining the steps you will take to improve